CONNECT

A Church Rebrand: The Hummingbird Ideas Case Study

How SFUMC refreshed its visual identity with a local design partner, from the first discovery exercise to the congregation rollout.

# The timeline

The rebrand ran a little over six months from decision to rollout, working with the designer Tim Dozier and Hummingbird Ideas:

| When | Step |
| --- | --- |
| August 26, 2024 | Church Council moves to pursue a brand refresh. |
| September 23, 2024 | Discovery exercise to define the church's identity before any design work. |
| March 24, 2025 | The new logo and visual identity are revealed to the Church Council. |
| March 28, 2025 | The new identity is rolled out to the congregation. |
| April 2025 | The branding is integrated into communications; the April brochure carries it. |

# What made it work

The church used a local design partner who started with discovery rather than jumping to a logo. Defining who the church is came first, and the visual identity followed from it. The reveal was sequenced deliberately: leadership saw it first, then the congregation a few days later, then it was integrated into the church's publications gradually rather than all at once.

# A caution on assets

When sharing a brand kit with other churches, curate it down to a usable example set and do not redistribute licensed fonts. The process is the transferable part; the specific assets belong to the church that commissioned them.

# How to use this

- Choose a designer who will run a discovery process, not just hand you a logo.

- Define the church's identity before approving any visual design.

- Reveal to leadership first, then the congregation, then integrate gradually.

- Budget the time: plan for roughly six months from decision to full rollout.